## Hoja1
Lenovo_Moto G55 5G (XT2433-5)_UOA34.216-174
discovery date | bug number | Raised in | Bug status | Fixed in | Fixed by | Tested by | Technology | Priority | Name | BUG DESCRIPTION | Comments & corrective actions | Defect ID QC
2024-08-07 | 1 | UOA34.210 | CLOSED | UOA34.216-89 | Prototype | Orange SP | DEDA | P1 | DEDA The device isn't in DEDA | Description: The device is not present in DEDA Steps to repro: 1.- Go to DEDA 2.- Go to Project > Oppo > Moto G35 5G Actual Result: The device has not been includes in DEDA Expected Result: DEDA should be completed with the device's data. | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: bug fixed | 11
2024-08-07 | 2 | UOA34.210 | CLOSED | UOA34.216-89 | Prototype | Orange SP | DEDA | P1 | DEDA The user manual is not available in DEDA | Description: The device don't have User Manual in DeDa Steps to repro: - Enter in DeDa web page and check that the device appears - Select device docs - Check that the User Manual is attached. Actual result: User Manual is not attached in DEDA . Expected result: The User Manual must be available on DeDa for this device. | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: bug fixed | 12
2024-08-07 | 3 | UOA34.210 | CLOSED | UOA34.216-89 | Prototype | Orange SP | DEDA | P1 | DEDA The TAC’s of the device is not available in DEDA | Description: The device doesn't have TAC. Steps to repro: - Enter in DeDa web page and check that the device appears - Select Product Header - Check that the TAC information is present. Actual result: The TAC information of the device in testing is not present in DEDA Expected result: The TAC must be available on DeDa for this device. | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: bug fixed | 13
2024-08-07 | 4 | UOA34.210 | CLOSED | UOA34.216-46 | Prototype | Orange SP | USABILITY | P1 | USABILITY Wrong device's name | Description: Device's name is wrong. Note: BT and USB are wrong too Steps to repro: 1. Go to settings > about the phone. 2. Check the name of the device. Actual result: Device's name is moto e22 Expected result: Device's name should be Moto G35 5G | Oesia comments (05/09/2024)[UOA34.216-46]: bug fixed | 14
2024-08-07 | 5 | UOA34.210 | CLOSED | UOA34.216-65 | Prototype | Orange SP | APP CENTER | P1 | APP CENTER Widget 2x1 HS | Description: Widget 2x1 is not displayed in the HS, only App Center is displayed. Steps to repro: 1. Do a Factory reset and finish the Wizard with an Orange SIM or Jazztel SIM. 2. Check if App Center and Widget 2x1 are displayed in HS. Actual result: Widget 2x1 is not displayed in the HS. Expected result: Widget 2x1 and App Center should displayed in the HS. Log: https://orangedevices.securevdr.com/public/share/web-s9e354c54b4b043e8ae311383c9fcb525 | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: bug fixed | 15
2024-08-07 | 6 | UOA34.210 | CLOSED | UOA34.216-46 | Prototype | Orange SP | IMS | P2 | IMS Call/Hand up VoWifi icon | Description: The Call/Hang up VoWiFi dialler icon is not correct when VoWifi is enable. Step to repro: 1- Register in a Wi-Fi network. 2- Check if you are registred in VoWifi 3- Make a VoWiFi call 4- Check dialler icon is correctly shown (call, hang) Actual result: The Call/Hang up VoWiFi dialler icon is not correct when VoWifi is enable: - Does not show the VoWifi icon on the dial pad to make a call. - Does not show the VoWifi icon on the call screen to end the call. Expected result: Call/Hang up VoWiFi dialler icon should display. | Oesia comments (05/09/2024)[UOA34.216-46]: design limitation | 16
2024-08-07 | 7 | UOA34.210 | CLOSED | UOA34.216-46 | Prototype | Orange SP | IMS | P2 | IMS HD icon in call history | Description: HD icon is displayed in call history after ending a VoLTE call Steps to repro: 1. Insert an Orange SIM with IMS active. 2. Go to play store and update all the apps. 3. Go to settings > SIM cards & mobile networks > Orange. 4. Check that 4G calls is active. 5. Do or receive a VoLTE call. 6. End the call, open the phone app and check the call history. Actual result: HD icon shows in call history after VoLTE call Expected result: HD icon should not show in call history | Oesia comments (05/09/2024)[UOA34.216-46]: design limitation | 17
2024-08-07 | 8 | UOA34.210 | OPEN |  | Prototype | Orange SP | SIM | P2 | SIM The EF SUME of the SIM card is not read by the device | Description: The EF SUME of the SIM card is not read by the device because the SIM TooLkit folder appears as Servicios SIM Steps to repro: 1. Insert a SIM with app SIM toolkit 2. Check the SIM Toolkit folder Actual Result: The device does not read correctly the EF SUME of the SIM card. Expected Result: The EF SUME of the SIM card has to be read by the device. The folder name should be "Orange Services" | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: it still happens Oesia comments (14/11/2024)[UOA34.216-108]: it still happens Oesia comments (09/12/2024)[UOA34.216-129-1]: it still happens Oesia comments (29/01/2025)[UOA34.216-174]: it still happens | 18
2024-08-08 | 9 | UOA34.210 | CLOSED | UOA34.216-174 | Prototype | Orange SP | NETWORK | P2 | 5G 5G+ Switch | Description: The switch to enable 5G+ are wrong with Jazztel/SIMYO SIM in devices with 5G SA enabled. Switch shows as "Vo5G - Use 5G for Voice Calls" Steps to repro: 1. Insert a Jazztel or SIMYO SIM 2. Go to Settings > Mobile Network > Mobile Data Actual result: Switch to enable 5G+ is displayed as "Vo5G - Use 5G for Voice Calls" Expected result: Switch to enable 5G+ shoud be "5G+" | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens, now we have 2 switch: - "Habilitar 5G SA", should be 5G+ - Vo 5G, this switch should disappear Oesia comments (17/10/2024)[UOA34.216-89]: pending to test when SA is enable, this version is not a 5G SA handset, so this bug cannot be check in this version Oesia comments (14/11/2024)[UOA34.216-108]: pending to test when SA is enable, this version is not a 5G SA handset, so this bug cannot be check in this version Oesia comments (09/12/2024)[UOA34.216-129-1]: pending to test when SA is enable, this version is not a 5G SA handset, so this bug cannot be check in this version Oesia comments (29/01/2025)[UOA34.216-174]: bug fixed | 19
2024-08-08 | 10 | UOA34.210 | OPEN |  | Prototype | Orange SP | USABILITY | P2 | USABILITY Data icon in toolbar when a MMS is send without mobile data | Description: An MMS sent without data is sent but does not show the 4G icon in the toolbar when it is sent. Steps to repro: 1. Insert a Orange SIM Card in the device. 2. Deactivate the data on the device and send an MMS. 3. Check if the data icon is displayed in the toolbar when the MMS is sent. Actual result: Data icon is not displayed in the toolbar when an MMS is sent without mobile data. Expected result: 4G icon should be displayed on the tollbar when an MMS is sent without mobile data. | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: it still happens Oesia comments (14/11/2024)[UOA34.216-108]: it still happens Oesia comments (09/12/2024)[UOA34.216-129-1]: it still happens Oesia comments (29/01/2025)[UOA34.216-174]: it still happens | 20
2024-08-08 | 11 | UOA34.210 | OPEN |  | Prototype | Orange SP | DUAL-SIM | P2 | DUAL SIM VoWifi icon in the toolbar | Description: In Dual SIM, VoWifi icon is only shown once or without identification if the sim that has activated VoWifi in the toolbar. If the two sims have activated VoWifi, it should be shown twice or once by putting an identifier on that icon of which sims are connected. Steps to repro: 1. Insert 2 sims in the device (a phisical sim and eSIM). 2. Active VoWifi in 2 sims and check if 2 icons or number are displayed in the toolbar when VoWifi is enabled. Actual result: When VoWifi is activated in dual SIM it is not known which sim or sims have enabled the function because it does not differ. Expected result: In dual SIMs, if the two sims have activated VoWifi, it should be shown twice or once by putting an identifier on that icon of which sims are connected. | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: it still happens Oesia comments (14/11/2024)[UOA34.216-108]: it still happens Oesia comments (09/12/2024)[UOA34.216-129-1]: it still happens Oesia comments (29/01/2025)[UOA34.216-174]: it still happens | 21
2024-08-08 | 12 | UOA34.210 | OPEN |  | Prototype | Orange SP | IMS | P2 | IMS First notification VoWifi call | Description: The first notification to VoWiFi services is not displayed in Orange, Jazztel and Simyo. Steps to repro: 1. Do a factory reset and finish the Wizard with a Ornage, Jazztel or Simyo SIM. 3. Ensure that appears a pop-ups information about VoWiFi setting or services (help menu). Actual result: First notification to VoWiFi services is not displayed Expected result: It should appear a pop-ups information about VoWiFi setting. Log: https://orangedevices.securevdr.com/public/share/web-s9e354c54b4b043e8ae311383c9fcb525 | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens, notification is displayed in Orange but it is in english and is not displayed in Jazztel and Simyo Oesia comments (17/10/2024)[UOA34.216-89]: it still happens, notification is displayed with Orange and Jazztel (not Simyo) but in english when you do a Factory reset, if Wizard is done without SIM, and you insert sim at the end, notification is correct. Log: https://orangedevices.securevdr.com/d-s1018d73e862c4c6581a2bcaea162d8f5 Miguel comments (23/10/2024): Downgrade to P2 for 25/10/2024 Conditioned TA Oesia comments (17/10/2024)[UOA34.216-89]: notification is displayed in English Oesia comments (14/11/2024)[UOA34.216-108]: it still happens, notification is displayed in English or not displayed Oesia comments (09/12/2024)[UOA34.216-129-1]: it still happens, notification is displayed in English or not displayed Oesia comments (29/01/2025)[UOA34.216-174]: still happens, notification is displayed but in English. Log: https://orangedevices.securevdr.com/public/share/web-sd83bbf5eef0947ec9aebdfd602ffe729 | 22
2024-08-08 | 13 | UOA34.210 | CLOSED | UOA34.216-174 | Prototype | Orange SP | USABILITY | P2 | USABILITY Mobile data in the Wizard | Description: Mobile data is not activated by default in the Wizard, it is only possible to activate it through an option shown at the end of the Wifi screen. Steps to repro: 1. Do a Factory reset and insert an Orange sim before the Wizard. 2. Check if mobile data is actived by default. Actual result: Mobile data is not activated by default in the Wizard Expected result: Mobile data should be activated by default because it is difficult to see this option and you will most likely pass the Wizard without data if Wi-Fi is not activated | Oesia comments (05/09/2024)[UOA34.216-46]: it still happens Oesia comments(17/09/2024)[UOA34.216-65]: it still happens Oesia comments (17/10/2024)[UOA34.216-89]: it still happens Oesia comments (14/11/2024)[UOA34.216-108]: it still happens Oesia comments (09/12/2024)[UOA34.216-129-1]: it still happens Oesia comments (05/02/2025)[UOA34.216-174]: design limitation | 23